SUPERVISOR'S GUIDE

Research Pipeline Oversight · Clinical Wellbeing Study · Q1 Publication Programme

PROJECT INFORMATION

Students: [Student 1 Name] ¦ [Student 2 Name]

Technical Consultant: AHSAN

Target Journal: Journal of Happiness Studies / Mindfulness / JCCP

Project Start Date: _______________

Focus: Wellbeing as treatment outcome in clinical populations

YOUR ROLE AS SUPERVISOR

Provide the initial domain brief (done — Clinical Wellbeing)

Review and approve the Stage 3 gap report

Co-design the research question in Stage 4

Approve preregistration before any data collection

Give manuscript feedback in Stage 7

Total time investment per cycle: 8-12 hours

KEY DECISION POINTS

Stage 3: Approve one of 5 gap candidates (must be clinically relevant)

Stage 4: Lock research question after gap approval

Stage 5: Approve preregistration before data collection

Do NOT allow data collection before preregistration — this is research misconduct

Last Updated: May 2026

SECTION 1 — PROJECT OVERVIEW FOR ALEV

The research pipeline has 7 stages. Your involvement is strategic, not continuous.

YOUR INVOLVEMENT BY STAGE

Stage 1-2: NO involvement — students work independently

Stage 3: REVIEW & APPROVE — gap report (2-3 hours)

Stage 4: CO-DESIGN — research question formulation (1 hour)

Stage 5: APPROVE — preregistration before data collection (1 hour)

Stage 6: NO involvement — students contact Ahsan for technical help

Stage 7: REVIEW — manuscript feedback (4-6 hours across 3 rounds)

You do NOT need to be involved in Stages 1, 2, 5 (execution), or 6 (Ahsan contact). Your total time investment per cycle is estimated at 8-12 hours.

SECTION 2 — STAGE 3 REVIEW: HOW TO EVALUATE THE GAP REPORT

2.1 WHAT STUDENTS MUST SUBMIT TO YOU

REQUIRED SUBMISSION ITEMS

☐ Search summary (databases used, article counts)

☐ Full article log (minimum 60 articles)

☐ Answers to all 8 trend analysis questions

☐ Gap classification matrix (3 columns)

☐ 5 gap candidates in full PICO-ready format

☐ Students' recommendation paragraph

☐ Time log

IF ANY ITEM IS MISSING

Return the report for completion before reviewing.

Do not accept partial submissions.

Set a 48-hour deadline for resubmission.

2.2 HOW TO EVALUATE THE 5 GAP CANDIDATES

Score each gap candidate using the criteria below. A score of 4.0+ indicates readiness to proceed.

GAP CANDIDATE #1

Gap Title:

__________________________________________________________________________

| Criterion | Weight | Your Score (1-5) | Weighted Score |
| --- | --- | --- | --- |
| Is this a genuine gap in the literature? | 25% | __ | __ |
| Is the proposed clinical population feasible? | 20% | __ | __ |
| Does this fit J Happiness Studies / Mindfulness / JCCP scope? | 20% | __ | __ |
| Is the methodology achievable within time/resource constraints? | 20% | __ | __ |
| Is the theoretical contribution clear? | 15% | __ | __ |
| TOTAL WEIGHTED SCORE | 100% | — | ___ |

Decision:

☐ Reject  ☐ Needs revision  ☐ Promising  ☐ APPROVED TO PROCEED

Your written feedback for students:

__________________________________________________________________________

__________________________________________________________________________

__________________________________________________________________________

GAP CANDIDATE #2

Gap Title:

__________________________________________________________________________

| Criterion | Weight | Your Score (1-5) | Weighted Score |
| --- | --- | --- | --- |
| Is this a genuine gap in the literature? | 25% | __ | __ |
| Is the proposed clinical population feasible? | 20% | __ | __ |
| Does this fit J Happiness Studies / Mindfulness / JCCP scope? | 20% | __ | __ |
| Is the methodology achievable within time/resource constraints? | 20% | __ | __ |
| Is the theoretical contribution clear? | 15% | __ | __ |
| TOTAL WEIGHTED SCORE | 100% | — | ___ |

Decision:

☐ Reject  ☐ Needs revision  ☐ Promising  ☐ APPROVED TO PROCEED

Your written feedback for students:

__________________________________________________________________________

__________________________________________________________________________

__________________________________________________________________________

GAP CANDIDATE #3

Gap Title:

__________________________________________________________________________

| Criterion | Weight | Your Score (1-5) | Weighted Score |
| --- | --- | --- | --- |
| Is this a genuine gap in the literature? | 25% | __ | __ |
| Is the proposed clinical population feasible? | 20% | __ | __ |
| Does this fit J Happiness Studies / Mindfulness / JCCP scope? | 20% | __ | __ |
| Is the methodology achievable within time/resource constraints? | 20% | __ | __ |
| Is the theoretical contribution clear? | 15% | __ | __ |
| TOTAL WEIGHTED SCORE | 100% | — | ___ |

Decision:

☐ Reject  ☐ Needs revision  ☐ Promising  ☐ APPROVED TO PROCEED

Your written feedback for students:

__________________________________________________________________________

__________________________________________________________________________

__________________________________________________________________________

GAP CANDIDATE #4

Gap Title:

__________________________________________________________________________

| Criterion | Weight | Your Score (1-5) | Weighted Score |
| --- | --- | --- | --- |
| Is this a genuine gap in the literature? | 25% | __ | __ |
| Is the proposed clinical population feasible? | 20% | __ | __ |
| Does this fit J Happiness Studies / Mindfulness / JCCP scope? | 20% | __ | __ |
| Is the methodology achievable within time/resource constraints? | 20% | __ | __ |
| Is the theoretical contribution clear? | 15% | __ | __ |
| TOTAL WEIGHTED SCORE | 100% | — | ___ |

Decision:

☐ Reject  ☐ Needs revision  ☐ Promising  ☐ APPROVED TO PROCEED

Your written feedback for students:

__________________________________________________________________________

__________________________________________________________________________

__________________________________________________________________________

GAP CANDIDATE #5

Gap Title:

__________________________________________________________________________

| Criterion | Weight | Your Score (1-5) | Weighted Score |
| --- | --- | --- | --- |
| Is this a genuine gap in the literature? | 25% | __ | __ |
| Is the proposed clinical population feasible? | 20% | __ | __ |
| Does this fit J Happiness Studies / Mindfulness / JCCP scope? | 20% | __ | __ |
| Is the methodology achievable within time/resource constraints? | 20% | __ | __ |
| Is the theoretical contribution clear? | 15% | __ | __ |
| TOTAL WEIGHTED SCORE | 100% | — | ___ |

Decision:

☐ Reject  ☐ Needs revision  ☐ Promising  ☐ APPROVED TO PROCEED

Your written feedback for students:

__________________________________________________________________________

__________________________________________________________________________

__________________________________________________________________________

2.3 FINAL DECISION

APPROVED GAP CANDIDATE

Approved Gap Candidate: #____ Title of approved gap: __________________________________________________________________________ Date of approval: __________________________________________________________________________ Next meeting date (Stage 4 question formulation): __________________________________________________________________________

SECTION 3 — KPI DASHBOARD FOR ALEV

Use this dashboard to track student progress at every stage. Review it at your weekly check-in.

3.1 STAGE 1 KPIs

| KPI | Target | Week 1 | Week 2 | Week 3 | Week 4 | Status |
| --- | --- | --- | --- | --- | --- | --- |
| Articles logged | 60 | __ | __ | __ | __ | [ ] |
| Databases searched | 7/7 | __ | __ | __ | __ | [ ] |
| Journals scanned | 12/12 | __ | __ | __ | __ | [ ] |
| Gap/weakness noted per article | 100% | __ | __ | __ | __ | [ ] |

3.2 STAGE 2 KPIs

| KPI | Target | Actual | Status |
| --- | --- | --- | --- |
| Trend questions answered | 8/8 | __ | [ ] |
| Gap matrix filled (min 3 per column) | 9 items | __ | [ ] |
| Gap candidates written in full | 5/5 | __ | [ ] |
| Recommendation paragraph written | Yes | __ | [ ] |

3.3 STAGE 3-5 KPIs

| KPI | Target | Actual | Date Completed | Status |
| --- | --- | --- | --- | --- |
| Report submitted to Alev | By agreed date | __ | __ | [ ] |
| Alev feedback given | Within 5 days | __ | __ | [ ] |
| Research question locked | After approval | __ | __ | [ ] |
| Preregistration submitted | Before data | __ | __ | [ ] |
| Power analysis completed | Before data | __ | __ | [ ] |
| Data collection started | After prereg | __ | __ | [ ] |
| Data collection completed | Per protocol | __ | __ | [ ] |
| First draft submitted | Per timeline | __ | __ | [ ] |

3.4 RED FLAGS — WHEN TO INTERVENE

| Red Flag | Action |
| --- | --- |
| Students have not logged 20 articles after 2 weeks | Schedule immediate check-in, review search strategy |
| Gap candidates are too vague or not based on literature | Return for full revision with written feedback |
| Students want to start data collection before preregistration | HARD STOP — do not allow this |
| Gap analysis looks copy-pasted or AI-generated without verification | Require students to defend each gap verbally |
| No contact from students for more than 7 days | Contact immediately — check for blocks |

SECTION 4 — WEEKLY CHECK-IN TEMPLATE

Hold a 30-minute weekly check-in with both students. Use this template.

WEEKLY CHECK-IN — WEEK 1

Date:

__________________________________________________________________________

| What did students complete this week? |  |
| --- | --- |
| What are they stuck on? |  |
| Did they contact Ahsan? If yes, for what? |  |
| On track with KPIs? | ☐ Yes ☐ Behind ☐ Significantly behind |
| Action items for next week: |  |
| Scope creep observed? | ☐ Yes ☐ No |
| If yes, describe and decision: |  |

WEEKLY CHECK-IN — WEEK 2

Date:

__________________________________________________________________________

| What did students complete this week? |  |
| --- | --- |
| What are they stuck on? |  |
| Did they contact Ahsan? If yes, for what? |  |
| On track with KPIs? | ☐ Yes ☐ Behind ☐ Significantly behind |
| Action items for next week: |  |
| Scope creep observed? | ☐ Yes ☐ No |
| If yes, describe and decision: |  |

WEEKLY CHECK-IN — WEEK 3

Date:

__________________________________________________________________________

| What did students complete this week? |  |
| --- | --- |
| What are they stuck on? |  |
| Did they contact Ahsan? If yes, for what? |  |
| On track with KPIs? | ☐ Yes ☐ Behind ☐ Significantly behind |
| Action items for next week: |  |
| Scope creep observed? | ☐ Yes ☐ No |
| If yes, describe and decision: |  |

WEEKLY CHECK-IN — WEEK 4

Date:

__________________________________________________________________________

| What did students complete this week? |  |
| --- | --- |
| What are they stuck on? |  |
| Did they contact Ahsan? If yes, for what? |  |
| On track with KPIs? | ☐ Yes ☐ Behind ☐ Significantly behind |
| Action items for next week: |  |
| Scope creep observed? | ☐ Yes ☐ No |
| If yes, describe and decision: |  |

SECTION 5 — MANUSCRIPT REVIEW GUIDE FOR ALEV

5.1 INTRODUCTION REVIEW CHECKLIST

INTRODUCTION

☐ Gap is clearly stated and supported by cited literature

☐ Research question is precise (population, variable, outcome, comparison)

☐ Hypotheses are stated directionally (not just 'we expect a relationship')

☐ Null hypothesis is also stated

5.2 METHOD REVIEW CHECKLIST

METHOD

☐ Preregistration DOI is cited

☐ Sample size is justified with power analysis numbers

☐ All measures are cited with Cronbach's alpha from original validation

☐ Procedure is replicable (someone else could run this study from this section)

☐ Manipulation check is described

5.3 RESULTS REVIEW CHECKLIST

RESULTS

☐ Effect sizes reported for every test (not just p-values)

☐ Bayesian Factor reported alongside frequentist tests

☐ Tables and figures are APA formatted

☐ Null results (if any) are framed as findings, not failures

5.4 DISCUSSION REVIEW CHECKLIST

DISCUSSION

☐ Opens with direct answer to the research question

☐ Null results (if any) are interpreted theoretically

☐ Limitations are honest and specific

☐ Future directions are concrete and tied to current gaps

SECTION 6 — JOURNAL SUBMISSION QUICK REFERENCE

| Journal | Acceptance Rate | Decision Time | Word Limit | Submission Link | Special Requirements |
| --- | --- | --- | --- | --- | --- |
| J Happiness Studies | 15-20% | 45-60 days | ~8000 words | springer.com/13158 | Preregistration preferred |
| Mindfulness | 25-30% | 45-60 days | ~8000 words | springer.com/12671 | Active control for interventions |
| JCCP | 20-24% | 60-90 days | ~7500 words | apa.org/pubs/journals/ccp | Preregistration for RCTs |
| BRAT | 15-20% | 60-90 days | ~7000 words | journals.elsevier.com/brat | Registered Reports accepted |
| CPS | 15-18% | 30-50 days | ~6000 words | journals.sagepub.com/cps | Bayesian analysis strongly preferred |

CONTACT INFORMATION

For technical support: Contact AHSAN

For research decisions: Contact Professor ALEV

For IT/AI automation: AHSAN can build custom tools

Document generated for the Clinical Wellbeing Research Pipeline. Last updated: May 2026